## Gantt Chart w % Complete
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Donation Data Visualization Project
| Gather Data/Form Ideas | 2019-10-14 | 14 | 2019-10-27 | 14 | 14 | 0 | Team | 100%
| Discuss technologies to be used | 2019-10-28 | 28 | 2019-11-03 | 7 | 3 | 4 | Team | 43%
| Become familiar with chosen technologies | 2019-11-04 | 4 | 2019-11-10 | 7 | 0 | 7 | Team | 0%
| Create Mockups of Graphs | 2019-11-11 | 11 | 2019-11-17 | 7 | 0 | 7 | Team | 0%
| Work on back-end, organizing the data | 2019-11-18 | 18 | 2019-11-27 | 10 | 0 | 10 | Team | 0%
| Work on displaying the data | 2019-11-28 | 28 | 2019-12-11 | 14 | 0 | 14 | Team | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1